## Product Backlog
AUAF Student Management System
Product Backlog
No | User Stories | Estimated Level of User Engagement | Priority | Sprint | Status
1 | As an administrator, I want to add my user account so that I can sign up in the system. | Low | Must | First | To be Completed
2 | As an administrator, I want to login into my account so that I can manage the system. | High | Must | First | To be Completed
3 | As an administrator, I want to have a management system so that the transactions go faster. | High | Must | First | To be Completed
4 | As an administrator, I want to create new user accounts so that I can have the information of my new users in my organization. | Medium | Must | First | To be Completed
5 | As an administrator, I want all users to log in using their usernames so that I can allow only authorized users to access the application’s features. | High | Must | First | To be Completed
6 | As an instructor, I want to add my user account so that I can sign up in the system. | Low | Should | First | To be Completed
7 | As an instructor, I want to login into my account so that I can manage my classes. | High | Must | First | To be Completed
8 | As a student, I want to add my user account so that I can sign up in the system. | Low | Should | First | To be Completed
9 | As a student, I want to login into my account so that I can manage my classes. | High | Must | First | To be Completed
10 | As a user, I want to have a navigation bar so that I can easily navigate through different tabs in the page. | High | Must | Second | To be Completed
11 | As an administrator, I want to remind students to pay their tuition fees on time so that I don’t put them on the stop list. | Medium | Should | Second | To be Completed
12 | As an administrator, I want to update students about their financial aids so that they can manage their fee installments on time. | Medium | Could | Second | To be Completed
13 | As an administrator, I want to review the users records so that I can give them promotion. | Medium | Won't | Second | To be Completed
14 | As an administrator, I want to edit the stop list so that I can remove the students after they paid their tuition fees. | High | Should | Second | To be Completed
15 | As an administrator, I want to change the course lists for each semester so that I can assign instructors for these courses. | Medium | Must | Second | To be Completed
16 | As an administrator, I want to add or remove the courses so that only I can finalize the courses according to the seats taken. | High | Must | Second | To be Completed
17 | As an administrator, I want to update the students’ progress, such as their major, concentration, and advisor so that they can follow up their work. | High | Must | Second | To be Completed
18 | As an administrator, I want to change the accounts’ settings so that I can manage the user accounts in case they forget their passwords. | Medium | Must | Second | To be Completed
19 | As an administrator, I want to have full access to the courses section so that I can add, delete, and update courses in case some changes are required. | Medium | Should | Second | To be Completed
20 | As an administrator, I want to access the user accounts so that I can track their records. | High | Should | Second | To be Completed
21 | As an administrator, I want to have a search bar so that I can view my users’ profiles. | High | Could | Second | To be Completed
22 | As an instructor, I want to access the students list so that I can view my students’ records. | Medium | Could | Third | To be Completed
23 | As an instructor, I want to access the students list so that I can know who registered in my classes. | Low | Must | Third | To be Completed
24 | As an instructor, I want to access the courses list so that I can offer and update the courses offered by me. | Low | Should | Third | To be Completed
25 | As an instructor, I want to access the programs list so that I can choose the programs that I can offer its classes. | Low | Won't | Third | To be Completed
26 | As an instructor, I want to access the students’ academic records so that I can submit their grades. | Medium | Must | Third | To be Completed
27 | As an instructor, I want to have a search bar in students list so that I can easily view the records of the student I search for. | High | Could | Third | To be Completed
28 | As an instructor, I want to access the list of users so that I can better know the command chain. | Medium | Won't | Third | To be Completed
29 | As an instructor, I want to enter the grades for each student so that I can enter their periodic grades, view their statistics, and update students’ grades for a course. | High | Must | Third | To be Completed
30 | As an instructor, I want to access my advisees list so that I can advise my advisees about their degree plans and courses. | Medium | Should | Third | To be Completed
31 | As an instructor, I want to authorize my advisee’s registration so that they can enroll themselves to the classes that they are eligible for. | Medium | Could | Third | To be Completed
32 | As an instructor, I want to have the registered students’ list in a course so that I can take their attendance. | High | Must | Third | To be Completed
33 | As an instructor, I want to add students’ violations records so that I can warn them about their violations. | Low | Won't | Third | To be Completed
34 | As an instructor, I want to view the waitlist for my classes so that I can change a students’ status when a seat becomes available. | Low | Could | Third | To be Completed
35 | As a student, I want to access my financial plan so that I can keep track of paying my fee installments on time. | High | Should | Third | To be Completed
36 | As a student, I want to access the courses list so that I can register myself to the courses I am eligible for. | High | Must | Third | To be Completed
37 | As a student, I want to print my academic records so that I can know my grades. | High | Must | Third | To be Completed
38 | As a student, I want to know who is my advisor so that I can take advice regarding my academic life. | Medium | Must | Third | To be Completed
39 | As a student, I want access the list of users so that I can better understand the chain of command. | Low | Could | Third | To be Completed
40 | As a student, I want to have a search bar for the courses list so that I can search easily the course I want to be registered. | High | Could | Third | To be Completed

## Project Details
Team Members | Role | Team | Project | Project Description | GitHub Repo | Date
Sayed Milad Fakhri | Product Owner | Team 02 | AUAF Student Management System | This project is a web application its goal is to make transactions go faster at AUAF. This Student Management System Web Application will have a login page and a dashboard containing a navigation bar in which the system administrators, instructors, and students can navigae through the Web Application to access information related to them and be capable of doing different feautres availbe for different types of user accounts. | https://github.com/SayedMiladFakhri/ITC-315---Scrum-Project---Team-02.git | November/10/2022
Ahmad Bilal Haidaree | Scrum Master
Sameera Aslami | Development Team
Nilofar Sohail | Development Team
Mohammad Abid Azamy | Development Team

## Legends
Estimated Level of User Engagement | Sprints | Priority (MosCow Method) | Explanation of the MoSCow Method
High (Level of User Engagement) | First | Must | Non-negotiable user stories that are mandatory for the product owner
Medium (Level of User Engagement) | Second | Should | Important user stories that are not vital, but add significant value
Low (Level of User Engagement) | Third | Could | Nice to have these user stories that will have a small impact if left out
|  | Won't | User Stories that are not priority for this specific time frame